## Sheet1
Month | Oct |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep
Week | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
Literature review
Models evaluation and comparison
Models derivation | [6 empty] | A
Code implementation of suspended droplet | [17 empty] | B
B.C's parametric analysis
OpenFOAM setup
OpenFOAM solver adaptation
OpenFOAM simulations
OpenFOAM solvers comparison | [40 empty] | F
Project plan report |  |  |  | α
Project progress report | [20 empty] | β
Project progress seminar | [31 empty] | γ
Project final report | [43 empty] | δ
Final seminar | [43 empty] | ε
| Literature | [13 empty] | Milestones | [15 empty] | Project plan report | [7 empty] | 11.11.22 |  |  |  | α
| Analytical Calculation | [13 empty] | Models selection | [9 empty] | A | [5 empty] | Project progress report | [7 empty] | 22.04.22 |  |  |  | β
| CFD Simulation | [13 empty] | Suspended droplet solution | [9 empty] | B | [5 empty] | Project progress seminar | [7 empty] | 14.06.22 |  |  |  | γ
| Analysis | [13 empty] | Parametric analysis completion | [9 empty] | C | [5 empty] | Project final report | [7 empty] | 11.10.23 |  |  |  | δ
| Holidays | [13 empty] | CFD results comparison | [9 empty] | F | [5 empty] | Project final seminar | [7 empty] | 12-15.10.23 |  |  |  | ε
Exams
Reports